## L5_L6_Schedule
Activity_ID | Activity_Name | Discipline | WBS_Path | L_Level | Planned_Start | Planned_Finish | Duration_Days | Predecessor_ID | Percent_Complete | Schedule_Status | Contractor
CIV-2200-0010 | Excavate Foundation - Compressor Bldg Grid A1-A4 | Civil | 1.2.3.1 | L5 | 2026-07-01 | 2026-07-05 | 5 |  | 100 | Complete | ABC Constructions
CIV-2200-0020 | Place PCC - Compressor Bldg Grid A1-A4 | Civil | 1.2.3.1 | L5 | 2026-07-06 | 2026-07-08 | 3 | CIV-2200-0010 | 100 | Complete | ABC Constructions
CIV-2200-0030 | Erect Rebar & Shutter - Foundation Grid A1-A4 | Civil | 1.2.3.1 | L5 | 2026-07-09 | 2026-07-14 | 6 | CIV-2200-0020 | 80 | In Progress | ABC Constructions
CIV-2200-0040 | Pour Concrete - Foundation Grid A1-A4 | Civil | 1.2.3.1 | L6 | 2026-07-15 | 2026-07-16 | 2 | CIV-2200-0030 | 0 | Not Started | ABC Constructions
PIP-3100-0110 | Fabricate Spool - Line 24-PL-1004-CS1A (Suction Hdr) | Piping | 1.4.2.3 | L5 | 2026-07-10 | 2026-07-13 | 4 |  | 100 | Complete | Precision Pipefab
PIP-3100-0120 | Erect Line 24-PL-1004-CS1A (Suction Hdr) Rack Section 3 | Piping | 1.4.2.3 | L5 | 2026-07-14 | 2026-07-17 | 4 | PIP-3100-0110 | 60 | In Progress | Precision Pipefab
PIP-3100-0130 | Weld Joints - Line 24-PL-1004-CS1A (Suction Hdr) Rack Sec 3 | Piping | 1.4.2.3 | L6 | 2026-07-18 | 2026-07-19 | 2 | PIP-3100-0120 | 0 | Not Started | Precision Pipefab
PIP-3100-0140 | Hydrotest - Line 24-PL-1004-CS1A (Suction Hdr) | Piping | 1.4.2.3 | L5 | 2026-07-20 | 2026-07-21 | 2 | PIP-3100-0130 | 0 | Not Started | Precision Pipefab
PIP-3100-0210 | Erect Line 10-PL-2051-CS2B (Discharge Hdr) Rack Section 1 | Piping | 1.4.2.4 | L5 | 2026-07-12 | 2026-07-15 | 4 |  | 100 | Complete | Precision Pipefab
EQP-4400-0310 | Set Compressor Skid C-101 on Foundation | Static/Rotating Equipment | 1.5.1.2 | L5 | 2026-07-17 | 2026-07-18 | 2 | CIV-2200-0040 | 0 | Not Started | HeavyLift Erectors
EQP-4400-0320 | Align & Grout Compressor Skid C-101 | Static/Rotating Equipment | 1.5.1.2 | L5 | 2026-07-19 | 2026-07-21 | 3 | EQP-4400-0310 | 0 | Not Started | HeavyLift Erectors
ELE-5500-0410 | Lay Power Cable - Compressor Bldg Feeder F-12 | Electrical | 1.6.2.1 | L5 | 2026-07-15 | 2026-07-17 | 3 |  | 30 | In Progress | Voltguard Electricals
ELE-5500-0420 | Terminate Power Cable - Feeder F-12 at MCC-03 | Electrical | 1.6.2.1 | L6 | 2026-07-18 | 2026-07-18 | 1 | ELE-5500-0410 | 0 | Not Started | Voltguard Electricals
INS-6600-0510 | Install Pressure Transmitter PT-2041 on Line 24-PL-1004 | Instrumentation | 1.7.1.5 | L6 | 2026-07-19 | 2026-07-19 | 1 | PIP-3100-0140 | 0 | Not Started | Sensorix Instruments
INS-6600-0520 | Loop Check - PT-2041 to DCS | Instrumentation | 1.7.1.5 | L6 | 2026-07-20 | 2026-07-20 | 1 | INS-6600-0510 | 0 | Not Started | Sensorix Instruments
HSE-7700-0010 | Toolbox Talk & Permit Issuance - Compressor Bldg Area | HSE | 1.8.1.1 | L6 | 2026-07-01 | 2026-07-21 | 21 |  | 70 | In Progress | Site HSE Team
CIV-2200-0050 | Backfill & Compaction - Foundation Grid A1-A4 | Civil | 1.2.3.1 | L5 | 2026-07-17 | 2026-07-19 | 3 | CIV-2200-0040 | 0 | Not Started | ABC Constructions