## Piping_Isometric_Log
Date | Line_No | Isometric_No | Spool_No | Activity_Desc | Location_Rack_Section | Status | Qty_Joints | Remarks | Reported_By
2026-07-10 | 24-PL-1004-CS1A | ISO-1004-07 | SP-1004-011 | Spool fabrication complete | Fab Yard | Done | - | Sent to site for erection | K. Iyer
2026-07-14 | 24-PL-1004-CS1A | ISO-1004-07 | SP-1004-011,012,013 | Spool erected on rack | Rack Sec 3 | In Progress | - | 3 of 5 spools placed | K. Iyer
2026-07-17 | 24-PL-1004-CS1A | ISO-1004-07 | SP-1004-011,012,013,014,015 | Spool erected on rack - section closed | Rack Sec 3 | Done | - | All spools placed, ready for tack/weld | K. Iyer
2026-07-18 | 24-PL-1004-CS1A | ISO-1004-07 | SP-1004-011 | Fit-up and tack weld | Rack Sec 3 | In Progress | 1 | Root pass pending, WPS-24-CS-01 | K. Iyer
2026-07-12 | 10-PL-2051-CS2B | ISO-2051-03 | SP-2051-004,005 | Spool erected on rack - section closed | Rack Sec 1 | Done | - | Discharge side, no issues | M. Verma
2026-07-20 | 24-PL-1004-CS1A | ISO-1004-07 | SP-1004-011,012,013,014,015 | Line ready for hydro, awaiting NDT clearance | Rack Sec 3 | Not Started | - | Blinds to be installed before test | K. Iyer
2026-07-21 | 10-PL-2051-CS2B | ISO-2051-04 | SP-2051-021 | New line identified - not in current schedule extract, please advise correct WBS tag | Rack Sec 2 (new tie-in) | Not Started | - | Client added tie-in scope on 19-Jul, awaiting planner mapping | M. Verma